## Agile Project Plan - BLANK
AGILE PROJECT PLAN FOR A PHARMACY SYSTEM
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| pharmacy system | Ali Zain Aldeen | 2020-06-24 | 2020-08-01 |  | 44% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Ali zain aldeen |  | 2020-06-24 | 2020-07-03 | 10 | completed
| design the ui for the system |  | Ali zain aldeen |  | 2020-06-24 | 2020-06-28 | 4 | completed
| design the ui for the insurance company system |  | Ali zain aldeen |  | 2020-06-29 | 2020-06-30 | 2 | completed
| design the databse |  | Razan al eter |  | 2020-06-28 | 2020-07-03 | 6 | completed
| Sprint 2 |  | Razan al eter |  | 2020-07-05 | 2020-07-15 | 11 | in progress
| implementing the database |  | Razan al eter |  | 2020-07-05 | 2020-07-11 | 7 | completed
| implenting the insurace company system |  | Ali zain aldeen |  | 2020-07-08 | 2020-07-15 | 8 | in progress
| Sprint 3 |  | Razan al eter |  | 2020-07-16 | 2020-08-01 | 17 | not started
| implenting the sales system |  | Ali zain aldeen |  | 2020-07-16 | 2020-07-28 | 13 | not started
| Fill out the database with the old records |  | Razan al eter |  | 2020-07-29 | 2020-08-01 | 4 | not started